## Timeline 18.04 - 27.05
STT | Sprint | Mã | Tên task | Phụ trách | Deadline | Deliverable / Ghi chú | Trạng thái
1 | S0 Đã xong | T0.1 | Nghiên cứu đề + soạn PROPOSAL capstone | Ân, Chuẩn, Lộc | 2026-04-05 | PROPOSAL DO AN MON HOC.docx | Done
2 | S0 Đã xong | T0.2 | Khởi tạo repo + cấu trúc 10 module + .gitignore | Chuẩn | 2026-04-05 | Repo init (commit d0a9b45) | Done
3 | S0 Đã xong | T0.3 | Docker Compose: mongo + license-server + cdn-sim | Ân | 2026-04-05 | infra/docker-compose.yml (commit deed33e) | Done
4 | S0 Đã xong | T0.4 | Nginx CDN-sim base: /video/ serve + /license reverse proxy + CORS | Ân | 2026-04-05 | cdn-sim/nginx.conf + Dockerfile (deed33e) | Done
5 | S0 Đã xong | T0.5 | License Server Express scaffold (GET /license stub) | Ân | 2026-04-05 | license-server/src/index.js stub (deed33e) | Done
6 | S0 Đã xong | T0.6 | ABR Encoding FFmpeg H.264 — 3 rendition 360p/720p/1080p (chưa segment fMP4, sẽ làm ở T2.1) | Chuẩn | 2026-04-14 | ingest/transcode.sh + transcode.ps1 + ingest/output/sample_{360,720,1080}p.mp4 (c59880a) | Done
7 | S0 Đã xong | T0.7 | README chi tiết: ngữ cảnh media + bài toán chống sao chép + kiến trúc mật mã + chi tiết AES/CENC/CTR/cbcs | Chuẩn | 2026-04-14 | README.md (ba05b41 + b987510 + 17a6792) | Done
8 | S0 Đã xong | T0.8 | Kịch bản tấn công & phòng thủ theo từng khối kiến trúc | Chuẩn | 2026-04-15 | Section tấn công trong README (ab6ea6c) | Done
9 | S0 Đã xong | T0.9 | Kịch bản tấn công User Flow (đăng ký, đăng nhập, session, API/DB) | Chuẩn | 2026-04-17 | Section User Flow trong README (fae987e) | Done
10 | S0 Đã xong | T0.10 | Sắp xếp + căn chỉnh sơ đồ kiến trúc trong README | Ân | 2026-04-18 | Commit f5c16f4, e02b173, 934fe41 | Done
11 | S1 Foundation | T1.1 | Họp phân công chi tiết + lock scope + GitHub Projects board | Ân, Chuẩn, Lộc | 2026-04-19 | Issue tracker + roadmap board | Done
12 | S1 Foundation | T1.2 | Cài shaka-packager + Bento4 vào Docker image (media-processing) | Lộc | 2026-04-20 | media-processing/Dockerfile chạy packager --version (fad73ad) | Done
13 | S1 Foundation | T1.3 | Script sinh Content Key (16B) + KID + IV bằng CSPRNG (README § T1.2) | Lộc | 2026-04-21 | media-processing/generate_cenc_keys.py + license_keys.json (fad73ad) | Done
14 | S1 Foundation | T1.4 | Schema MongoDB + migrate init (kids, content_keys_enc, users, entitlements, devices, sessions) | Chuẩn | 2026-04-20 | database/schema.md + file migrate (CHƯA TẠO — folder database/ trống) | Pending
15 | S1 Foundation | T1.5 | Module JWT issue/verify (HS256 + RS256) cho License Server | Chuẩn | 2026-04-21 | license-server/src/auth/jwt.js + unit test (CHƯA TẠO) | Pending
16 | S1 Foundation | T1.6 | Hardening nginx: Range request, gzip off cho .m4s, chuẩn bị TLS (README § T1.6) | Ân | 2026-04-20 | cdn-sim/nginx.conf + test-range.sh + gen-selfsigned-cert.sh (90d7610) | Done
17 | S1 Foundation | T1.7 | Scaffold Player (Vite + Shaka Player) + UI skeleton (README § T1.7) | Ân | 2026-04-21 | player/ chạy npm run dev, useShakaPlayer hook + mocks (fb15c3b) | Done
18 | S2 Core Crypto | T2.1 | Packager CENC AES-128-CTR encrypt 3 rendition + manifest .mpd (README § T1.3) | Lộc | 2026-04-25 | packager/output/*.m4s + manifest.mpd có ContentProtection PSSH (fcc4a4f) | In Progress | Chạy lại packager lệnh đầy đủ (script đã in sẵn trong generate_cenc_keys.py) với video_1080p.mp4 + audio.m4a đặt cạnh script, để sinh media-processing/output/{360p,720p,1080p,audio}_init.mp4 + *_$Number$.m4s. Sau đó cdn-sim mount mới (vốn :ro) sẽ phục vụ đúng segment encrypted, Player load /video/manifest.mpd sẽ kích hoạt EME thật → khi đó T2.1 mới chính thức Done
19 | S2 Core Crypto | T2.2 | Kiểm tra box tenc/sinf/pssh bằng mp4dump (Bento4) (README § T1.5) | Lộc | 2026-04-27 | Log xác nhận defaultIsProtected=1, defaultPerSampleIVSize=8, defaultKID khớp KMS (fcc4a4f) | Done
20 | S2 Core Crypto | T2.3 | Key Rotation 30 phút (4 Period cho video 2h) | Lộc | 2026-04-28 | media-processing/output/manifest_rotation.mpd — multi Period, 4 Key khác nhau (67ca7b3) | In Progress | Đã có multi-key/PoC nhưng chưa multi-Period theo thời gian → cần tách Period nối tiếp khớp README Hướng đi là refactor generate_cenc_keys.py để dùng input clip dài hơn + để packager tự sinh <Period> nối tiếp, hoặc tạo manifest thủ công có nhiều <Period>
21 | S2 Core Crypto | T2.4 | License Server POST /license (pssh+jwt) + entitlement check Mongo (README § T1.4) | Chuẩn | 2026-04-25 | Endpoint 200/403 theo quyền — license-server hiện vẫn là GET stub | In Progress
22 | S2 Core Crypto | T2.5 | Mã hóa Content Key trong License Response bằng RSA-OAEP (README § T1.4) | Chuẩn | 2026-04-27 | encryptKey(pubKey, contentKey) + test vector — chưa có module | In Progress
23 | S2 Core Crypto | T2.6 | KMS at-rest AES-256-GCM + nonce chống replay + time-bound license | Chuẩn | 2026-04-28 | license-server/src/kms/ + exp + nonce store | Pending
24 | S2 Core Crypto | T2.7 | Player load manifest CDN dry-run clear (local cdn-sim → /video/manifest.mpd) (README § T1.7) | Ân | 2026-04-25 | player/src/mocks/manifests.ts mục local-cdn-sim + useShakaPlayer load OK | Done
25 | S2 Core Crypto | T2.8 | Player EME request → /license → play content mã hóa Widevine L3 (README § T1.7) | Ân | 2026-04-28 | Demo Chrome play encrypted OK — chờ T2.4/T2.5 wire license-server | In Progress
26 | S3 Integration | T3.1 | Integration test E2E: ingest → packager → CDN → player → license (README § F) | Ân, Chuẩn, Lộc | 2026-05-01 | infra/smoke-test.sh pass xanh | Pending
27 | S3 Integration | T3.2 | TLS 1.3 + HSTS + self-signed cert; Player cert pinning (README § T1.4 / T1.6) | Ân | 2026-05-02 | cdn-sim https:// hoạt động + cert pinning client | Pending
28 | S3 Integration | T3.3 | Player UI: controls, seek (random access CTR), ABR switch, log panel (README § T1.7) | Ân | 2026-05-05 | UI demo-ready cho thuyết trình | Pending
29 | S3 Integration | T3.4 | License session control (max 2 device đồng thời) + audit log Mongo (README § Quản lý quyền) | Chuẩn | 2026-05-02 | Device thứ 3 bị từ chối; collection licenses_audit | Pending
30 | S3 Integration | T3.5 | Master Key rotation API + re-encrypt Content Key | Chuẩn | 2026-05-05 | POST /kms/rotate + test rotation | Pending
31 | S3 Integration | T3.6 | PoC E1 — download segment bằng wget → ffplay thất bại (README § E1) | Lộc | 2026-05-03 | Script + log ciphertext không phát/ghép được | Pending
32 | S3 Integration | T3.7 | PoC E2 — IV Reuse attack: XOR 2 ciphertext cùng key/IV (README § E2) | Lộc | 2026-05-05 | poc/iv-reuse.py + screenshot khôi phục plaintext | Pending
33 | S4 Attacks + WM | T4.1 | PoC E3 — Key Extraction Widevine L3 bằng Frida (Chrome) (README § E3) | Lộc | 2026-05-09 | Script Frida + dump key console | Pending
34 | S4 Attacks + WM | T4.2 | PoC E5 — License Replay (capture → replay → từ chối, Nonce 1 lần) (README § E5) | Lộc | 2026-05-11 | Log 401/403 Nonce expired | Pending
35 | S4 Attacks + WM | T4.3 | Benchmark E6 — AES-128-CTR throughput có/không AES-NI (README § E6) | Chuẩn | 2026-05-09 | benchmarks/aes-throughput.md + biểu đồ MB/s | Pending
36 | S4 Attacks + WM | T4.4 | Benchmark License latency p50/p95/p99 (k6 / autocannon) (README § Metrics) | Chuẩn | 2026-05-12 | benchmarks/license-latency.md + raw k6 | Pending
37 | S4 Attacks + WM | T4.5 | Watermark embed — User ID vào DCT tần số trung bình (Python) (README § E7) | Ân | 2026-05-09 | watermark/embed.py chạy với sample | Pending
38 | S4 Attacks + WM | T4.6 | Watermark detect + robustness (re-encode, crop, blur, rotate) (README § E7) | Ân | 2026-05-12 | watermark/detect.py + bảng recall/precision | Pending
39 | S4 Attacks + WM | T4.7 | E7 — tổng hợp hạn chế watermark (collusion, analog re-capture) (README § Watermarking) | Ân | 2026-05-12 | Section report + slide | Pending
40 | S5 Hardening | T5.1 | Package thêm scheme cbcs cho HLS (FairPlay compat) — handshake SPC/CKC tối thiểu (README § E8) | Lộc | 2026-05-16 | output-hls/master.m3u8 chạy Safari + tài liệu SPC/CKC | Pending
41 | S5 Hardening | T5.2 | Docs pipeline packager — docs/packager.md có ví dụ lệnh | Lộc | 2026-05-19 | Markdown + screenshot output | Pending
42 | S5 Hardening | T5.3 | Unit + integration test License Server (Jest + supertest) | Chuẩn | 2026-05-16 | Coverage >= 70% auth/kms/license | Pending
43 | S5 Hardening | T5.4 | API spec OpenAPI/Swagger + docs/license-server.md | Chuẩn | 2026-05-19 | openapi.yaml + swagger UI | Pending
44 | S5 Hardening | T5.5 | Benchmark Time-to-First-Frame: DRM vs no-DRM (README § Metrics) | Ân | 2026-05-16 | Bảng số liệu + biểu đồ | Pending
45 | S5 Hardening | T5.6 | Hoàn thiện docker-compose: 1 lệnh up toàn hệ (README § F) | Ân | 2026-05-17 | README run từ máy sạch OK | Pending
46 | S5 Hardening | T5.7 | docs/player.md + docs/architecture.md (sơ đồ tổng) | Ân | 2026-05-19 | 2 file md + diagram mermaid/ảnh | Pending
47 | S6 Delivery | T6.1 | Tổng duyệt demo E2E + fix bug còn đọng (README § F) | Ân, Chuẩn, Lộc | 2026-05-22 | Checklist demo 100% pass | Pending
48 | S6 Delivery | T6.2 | Slide: ngữ cảnh media + kiến trúc + demo (5-7 slide) (README § R) | Ân | 2026-05-24 | File slide nhánh report/ | Pending
49 | S6 Delivery | T6.3 | Slide: license flow + attack/defense + benchmark (5-7 slide) (README § R) | Chuẩn | 2026-05-24 | File slide | Pending
50 | S6 Delivery | T6.4 | Slide: CENC + segment design + watermark + PoC attack (5-7 slide) (README § R) | Lộc | 2026-05-24 | File slide | Pending
51 | S6 Delivery | T6.5 | Quay demo video backup (OBS) + kịch bản live demo | Ân, Chuẩn, Lộc | 2026-05-26 | File mp4 + kịch bản | Pending
52 | S6 Delivery | T6.6 | Review README + hoàn thiện docs/ + cập nhật link Timeline (README § R) | Ân | 2026-05-26 | README final, không còn TODO | Pending
53 | S6 Delivery | T6.7 | Tổng duyệt cuối + nộp sản phẩm (README § R) | Ân, Chuẩn, Lộc | 2026-05-27 | Nộp đúng hạn 27/05/2026 | Pending

## Tiến độ
TIẾN ĐỘ TỔNG QUAN
Chỉ số | Giá trị
Tổng số task | 53
Đã xong (Done) | 17
Đang làm (In Progress) | 5
Chưa bắt đầu (Pending) | 31
Bị chặn (Blocked) | 0
Quá deadline chưa xong | 12
% Hoàn thành | 0%
Hôm nay | 2026-05-05 | Deadline cuối | 2026-05-27
Còn lại (ngày) | 22
TIẾN ĐỘ THEO NGƯỜI
Người | Tổng | Done | Còn lại | % Done
Ân | 24 | 9 | 15 | 37.5%
Chuẩn | 23 | 7 | 16 | 30.43%
Lộc | 18 | 5 | 13 | 27.78%
TIẾN ĐỘ THEO SPRINT
Sprint | Tổng | Done | Còn lại | % Done
S0 | 10 | 10 | 0 | 100%
S1 | 7 | 5 | 2 | 71.43%
S2 | 8 | 2 | 6 | 25%
S3 | 7 | 0 | 7 | 0%
S4 | 7 | 0 | 7 | 0%
S5 | 7 | 0 | 7 | 0%
S6 | 7 | 0 | 7 | 0%